## Table 1
RBS (Fusion) - Confluence UAT Acceptance Form Purpose of this UAT is to verify that all elements of the test system have been checked by RBS (Fusion) and that there is agreement that the Upgrade can proceed into the production environment
Project Name | PS-19439 - RBS (Fusion): Enterprise Engineering Future Tools: Upgrade Add-on (2020/2021) IN PROGRESS
Effective Date | 2020-08-13
Customer Name | RBS (Fusion)
Customer Key Contact(s) | Mohit Bansal <Mohit.Bansal1@rbs.co.uk>
Confluence Test Elements |  | Result | Date | Name | Comments
Check the service is up and ok:
Check Confluence service is running
Inspect Confluence log at <confluence->/logs/atlassian-confluence.log (Linux) or <confluence- home>\logs\atlassian-confluence.log for errors
Login to Confluence via the URL usually either http(s)://'server-name':8090 or http(s)://'server-name':8090 /confluence or the URL defined in DNS
Once on the Service as an admin user:
Check spaces exist and are available
Drill down into a couple of spaces to ensure pages are available
Open some pages to make sure they are available and have correct content
Click on attachments and links in pages to ensure they are loading correctly
Check the base URL is correct (From Admin Screen)
Run a few searches to make sure a search re-index is not required, if it is it can take several hours and affect performance
Check the mail server configuration OS correctly set up
Make sure add-ons are up to date and still compatible with the version you are running
If on a version of 6+ ensure collaborative editing is set as the business requires
Check under content indexing that the queue contents are processing or idle
Check the cache's are performing as expected and flush as necessary
Check the application links are connected and click the link to make sure it's active
Check the analytics are enabled/disabled as required
Click the support tools and check the instance health and log analyser and take any necessary actions
Check the user directories to ensure they are in the correct order and are available
Ensure space and global permissions are setup as expected
Move to user management and ensure all expected users are on the system and are enabled
Make sure performance is as expected and change the java setting as required. ( https://confluence.atlassian.com/adminjiraserver071/increasing-jira-application- memory-802592945.html)
Once on the service as a normal service user:
Check Space directory to ensure the expected spaces are available
Drill down into a couple of spaces to make sure the pages are available and accessible
Click on any links or attachments within the spaces to make sure they are accessible
Ensure the profile looks as it should
Check all the spaces that could be accessed can still be accessed
Test Search
Create a Space
Create Page
Add Attachment
Test and Macros/Plugins expected
Delete Page and Space
Logout

## Table 2
Declaration By signing-off this document RBS (Fusion) agrees to allow Clearvision to further progress to the next stage of the production. The customer now agrees that any subsequent defects that discovered during the live migration and may require further time and materials, may be chargeable
Customer Name
Position
Signature
Date
Any further comments